# Sprint Burndown Trajectory & Variance Analysis

Phase 10 Deliverable: Scrum Metrics - 24CYS401 Lab Examination

# 1. Sprint Burndown Trajectory Analysis

Burndown tracking measures remaining story points against the ideal linear progress guideline across the 10-day sprint cycles.

# 2. Sprint 1 Burndown Analysis

Day 1-4: Progress closely tracked ideal slope with steady completion of DWPG-10 (Auth) and DWPG-11 (Wallet).
Day 5-7: Core payments completed (DWPG-13, 8 SP).
Day 8: DEF-001 discovered during concurrency tests, causing the burndown curve to plateau at 5 remaining story points. The team completed Sprint 1 with 21 SP burned down and 5 SP carried over.

# 3. Sprint 2 Burndown Analysis

Day 1-3: Rapid burn down of DEF-001 (5 SP) and DWPG-16 (Pessimistic Locking, 5 SP).
Day 4-6: Completion of Idempotency filter (DWPG-17) and Refund service (DWPG-18).
Day 7-10: Completion of containerization, CI/CD pipeline, and final testing. Sprint 2 achieved complete burndown of all 34 committed story points to zero on Day 10.