## Sprint Velocity Report
Sprint Name | Sprint ID | Goal | Committed SP | Completed SP | Carried Over SP | Defects Discovered | Defects Fixed
DWPG Sprint 1 - Core Pay | 79 | Build secure core wallet and payment functionality | 26 | 21 | 5 | 1 | 0
DWPG Sprint 2 - Hardening | 80 | Complete security hardening, testing, containerization, and DEF-001 resolution | 34 | 34 | 0 | 0 | 1
TOTAL / AVERAGE | - | Two-Sprint Delivery Cadence | 60 | 55 | 0 | 1 | 1