## Product Backlog
Jira Key | Story ID | Epic | Priority | User Story Description | Story Points | Sprint Allocation | Acceptance Criteria | Security Acceptance Criteria
DWPG-10 | STORY-01 | EPIC-01: Authentication | High | As a user, I want to register and authenticate securely so that I can access my digital wallet. | 5 | Sprint 1 | POST /api/auth/register, POST /api/auth/login | BCrypt factor 12, HMAC-SHA256 JWT, generic error messages
DWPG-11 | STORY-02 | EPIC-02: Wallet Management | High | As a user, I want a digital wallet provisioned and the ability to add simulated funds so that I have a balance to make purchases. | 5 | Sprint 1 | Auto wallet creation with bash.00, POST /api/wallets/fund | BOLA check (owner only), balance ceiling, positive decimals
DWPG-12 | STORY-03 | EPIC-03: Merchant Management | Medium | As a merchant, I want to register my merchant business so that I can receive customer payments. | 3 | Sprint 1 | POST /api/merchants registers business, creates merchant ID & wallet | Requires ROLE_USER or ROLE_MERCHANT, XSS sanitization
DWPG-13 | STORY-04 | EPIC-04: Payment Processing | Highest | As a user, I want to initiate and confirm payments to merchants so that I can purchase simulated goods. | 8 | Sprint 1 | POST /api/payments creates payment, debits sender, credits merchant | Non-negative balance enforcement, atomic state FSM
DWPG-14 | STORY-05 | EPIC-06: Security & Audit | High | As an administrator, I want basic transactional audit logging so that all debits and credits are recorded. | 5 | Sprint 1 | Audit log records created on logins and payments | Append-only audit table, sensitive token scrubbing
DWPG-15 | DEF-001 | EPIC-06: Security & Audit | Highest | BUG: Duplicate payment accepted when idempotency key was not enforced; race condition allows double spending. | 5 | Sprint 1 -> 2 | Carried over from Sprint 1 to Sprint 2 for comprehensive fix | Pessimistic row locking (SELECT ... FOR UPDATE) & Idempotency key
DWPG-16 | STORY-06 | EPIC-06: Security & Audit | Highest | As a user, I want pessimistic row locking on wallet balances so that concurrent payments cannot cause double-spending or negative balances. | 5 | Sprint 2 | Pessimistic write locking on DB rows during payment | Zero double spending under concurrency stress test; DB check constraint
DWPG-17 | STORY-07 | EPIC-06: Security & Audit | Highest | As a payment gateway, I want mandatory Idempotency-Key enforcement with SHA-256 payload binding so that replayed payments return cached response. | 5 | Sprint 2 | Mandatory Idempotency-Key header; identical payload returns cached response | Tampered payload with reused key triggers REPLAY_DETECTED alert (409 Conflict)
DWPG-18 | STORY-08 | EPIC-05: Refunds & Transactions | High | As a merchant, I want to issue refunds on confirmed transactions so that dissatisfied customers receive their funds back. | 5 | Sprint 2 | POST /api/payments/{id}/refund reverses funds atomically | Only merchant owner can refund; status must be CONFIRMED; duplicate refund blocked
DWPG-19 | STORY-09 | EPIC-05: Refunds & Transactions | Medium | As a user and merchant, I want to view my immutable transaction history ledger so that I have a complete financial audit record. | 3 | Sprint 2 | GET /api/transactions returns paginated ledger entries | BOLA protection ensures users cannot view foreign transaction ledgers
DWPG-20 | STORY-10 | EPIC-06: Security & Audit | High | As an administrator, I want to inspect security audit logs and receive alerts on replay and double-spending attempts so that fraudulent behavior is investigated. | 5 | Sprint 2 | GET /api/admin/audit-logs and GET /api/admin/alerts return security events | Strict ROLE_ADMIN verification; unprivileged users receive 403 Forbidden
DWPG-21 | STORY-11 | EPIC-07: DevSecOps | Medium | As a DevSecOps engineer, I want containerized Docker images and Kubernetes manifests with non-root security contexts so that the gateway runs securely in production. | 3 | Sprint 2 | Multi-stage Docker build, non-root user (UID 10001), K8s manifests | Resource quotas, dropped capabilities, no baked-in secrets
DWPG-22 | STORY-12 | EPIC-08: Testing & Quality | High | As a QA engineer, I want automated unit, integration, concurrency, rollback, and fuzzing test suites in CI so that regressions are automatically blocked. | 3 | Sprint 2 | Automated test suite passing in CI; 100% pass on security test suite | Zero vulnerabilities in SonarQube SAST scan